## EVM
CTAF — Earned Value Management (misure in story point)
Sprint | EV (SP) | PV (SP) | AC (SP) | SPI = EV/PV | CPI = EV/AC | SV = EV-PV | CV = EV-AC
Sprint 1 | 18 | 20 | 18
Sprint 2 | 18 | 22 | 18
Sprint 3 | 16 | 18 | 16
Sprint 4 | 15 | 18 | 15
Cumulativo
Note:
• EV=Earned Value, PV=Planned Value, AC=Actual Cost (qui in story point; costo in EUR = 0).
• SPI<1 = in ritardo sullo schedule; CPI=1.00 perche il costo monetario e nullo.
• SV (Schedule Variance) e CV (Cost Variance) in story point.